## Sheet1
iPRIMED Defect Tracker Template
iPRIMED Education Solutions Pvt Ltd #628,Majestic Terraces, Second Floor Electronic city Phase I,Bangalore-560100
ID | Test Env | Status (New / Open / InProgress / Fixed / Closed / Reopen) | Assigned To | REQ# (Sprint Number) | Description | Severity (Critical, Major, Minor, Cosmetic) | Priority (High / Medium / Low) | Developer | Comments | Tested Date | Tested By | Verified By | Verified Date | Defect Type | Technical Analysis
1 | design | Fixed | sc@lululemon.com | Sprint 1 | Proposed title alteration | major | Medium |  | -- | 2023-10-30 | Shravya C |  | 2023-11-03 | non-functional
2 | design | Fixed | hsaravanan@lululemon.com | Sprint 1 | To alter the goal of Returns Reduction Project | major | Medium |  |  | 2023-10-30 | Harini Saravanan |  | 2023-11-03 | functional
3 | design | Fixed | sta3@lululemon.com | Sprint 1 | To add flowcharts with respect to admin and user for retail store inventory | major | Medium |  |  | 2023-10-30 | Sheethal T A |  | 2023-11-04 | functional
4 | design | Fixed | nmp@lululemon.com | Sprint 1 | To have an overall discussion with the team about the implemnatation of the project | major | high |  |  | 2023-10-30 | Nanditha M P |  | 2023-11-04 | functional
5 | development | Fixed | nmishra@lululemon.com | Sprint 2 | To add the validation for email by sending otp to the users | major | high |  |  | 2023-11-09 | Nilay,Shravya C |  | 2023-11-12 | functional
6 | development | Fixed | sc@lululemon.com | Sprint 2 | To provide a span of 10 days for the users to return any products purchased | major | high |  |  | 2023-11-09 | All team members |  | 2023-11-12 | functional