## Team Members
No | Name | Role
1 | Shravya C | Scrum Master
2 | Harini Saravanan | Team Members
3 | Sheethal T A | Team Members
4 | Nilay Mishra | Team Members
5 | Nanditha M P | Team Members

## Scrum meetings
Dates | Shravya C | Harini Saravanan | Sheethal T A | Nilay Mishra | Nanditha M P | Status/Update | Remark
20/10/2023 | Creating understanding in PPt or document from the Case study document | Creating understanding in PPt or document from the Case study document | Creating understanding in PPt or document from the Case study document | Creating understanding in PPt or document from the Case study document | Creating understanding in PPt or document from the Case study document | Completed
30/10/2023 | Completed the kick-start call with the client,they gave some review,we are working on that | Completed the kick-start call with the client,they gave some review,we are working on that | Completed the kick-start call with the client,they gave some review,we are working on that | Completed the kick-start call with the client,they gave some review,we are working on that | Completed the kick-start call with the client,they gave some review,we are working on that | Completed
31/10/2023 | Working on designing phase | Working on designing phase | Working on designing phase | Working on designing phase | Working on designing phase | Working
2023-02-11 | Trying to complete design part with in today | Trying to complete design part with in today | Trying to complete design part with in today | Trying to complete design part with in today | Trying to complete design part with in today | Completed | Make sure of start implemntation from tomorrow
2023-03-11 | Implementation of login and logout page | Implementation of login and logout page | Implementation of login and logout page | Implementation of login and logout page | Implementation of login and logout page | Completed
2023-06-11 | Working on Catalogue case | Working on Cart case | Working on inventory case | Working on payment case | Working on Confirmation case | Working
2023-07-11 | Working on Catalogue case | Working on Cart case | Working on inventory case | Working on payment case | Working on Confirmation case | Completed
2023-08-11 | Working on API Gateway | Working on Returns Management Case | Working on Product Case | Working on Registry Case | Working on Customer Case | Working
2023-09-11 | Working on API Gateway /Exception | Working on Returns Management Case/TestCases | Working on Product Case/TestCase | Working on Registry Case/TestCases | Working on Customer Case /TestCases | Completed
2023-10-11 | As mentioned almost covered 75% work and preparing for Sprint call-2 | As mentioned almost covered 75% work and preparing for Sprint call-2 | As mentioned almost covered 75% work and preparing for Sprint call-2 | As mentioned almost covered 75% work and preparing for Sprint call-2 | As mentioned almost covered 75% work and preparing for Sprint call-2 | Completed
13/11/23 | Today working on feedback received during srum call implemneting authorization for order managemnet. | Undersatnding the flow of project and working on authorization code | Today working on feedback received during srum call implemneting authorization for product managemnet. | Today working on feedback received during srum call implemneting authorization for user registration details. | Today working on feedback received during srum call implemneting authorization for login. | Working
15/11/23 | Today working on feedback received during srum call implemneting authorization for order managemnet. | Undersatnding the flow of project and working on authorization code | Today working on feedback received during srum call implemneting authorization for product managemnet. | Today working on feedback received during srum call implemneting authorization for user registration details. | Today working on feedback received during srum call implemneting authorization for login. | Completed
16/11/23 | Successfully authenticated and progressing further. | Completed with spring security and moving forward | Completed with spring security and moving forward | Completed with spring security and moving forward | Completed with spring security and moving forward | Completed
17/11/23 | Successfully completed the project | Successfully completed the project | Successfully completed the project | Successfully completed the project | Successfully completed the project | Completed
20/11/23 | Uploading all the codes into the folder and getting ready for final presentation | Working on test cases document and getting ready for final presentation | Working on traceability document and getting ready for final presentation | Working on final presentation ppt | Uploading all the codes into the folder and getting ready for final presentation | Completed

## Sheet3
TO BE FILLED EVERY HOUR ON A DAILY BASIS
Team Names | Participant Name | Date | Action Items by the participant | Overall Team's action item for the day(reviewed by Amit) List down the action items performed by the team | overall team review from Tech Architect Review and feedback of code given to each of the participant Review by Amit
Team C | Shravya C | 31/10/2023 | Use case diagram
Team C | Harini Saravanan | 31/10/2023 | ER Diagram
Team C | Sheetal T A | 31/10/2023 | Architecture
Team C | Nanditha M P | 31/10/2023 | Class Diagram
Team C | Nilay Mishra | 31/10/2023 | Object Diagram
Team C | Shravya C | 2023-02-11 | Object Diagram
Team C | Harini Saravanan | 2023-02-11 | Use case diagram
Team C | Sheetal T A | 2023-02-11 | DB diagram
Team C | Nanditha M P | 2023-02-11 | Use case diagram
Team C | Nilay Mishra | 2023-02-11 | ER Diagram
Team C | Shravya C | 2023-03-11 | Working on login page of client
Team C | Harini Saravanan | 2023-03-11 | Working on login page of client
Team C | Sheetal T A | 2023-03-11 | Working on login page of admin
Team C | Nanditha M P | 2023-03-11 | Working on login page of admin
Team C | Nilay Mishra | 2023-03-11 | Working on login page of admin
Team C | Shravya C | 2023-06-11 | Working on Catalogue | Working on Various implementations, Working on CRUD Operations Using Microservice Architecture | Going Good
Team C | Harini Saravanan | 2023-06-11 | Working on Cart |  | Going Good
Team C | Sheetal T A | 2023-06-11 | Working on Inventory |  | Going Good
Team C | Nanditha M P | 2023-06-11 | Working on payment |  | Going Good
Team C | Nilay Mishra | 2023-06-11 | Not well, so unable to work |  | Not Keeping Well,Do it Later
Team C | Shravya C | 2023-07-11 | Working on Catalogue | Working on Various implementations, Working on CRUD Operations Using Microservice Architecture
Team C | Harini Saravanan | 2023-07-11 | Working on Cart
Team C | Sheetal T A | 2023-07-11 | Working on Inventory
Team C | Nanditha M P | 2023-07-11 | Working on payment
Team C | Nilay Mishra | 2023-07-11 | Not well, so unable to work
Team C | Shravya C | 2023-08-11 | Working on API Gateway /TestCases | The team has completed CRUD operations on key requirements, including Order Management, Product and Promotions Management, Retail Store Inventory Management, Product Specifications, and Shipping Details, along with Login, Registration, API Gateway, and Registry. So far, 5 use cases have been completed, and 6 use cases are in progress. The goal is to complete a total of 11 use cases and then begin working on the logical r equirements and their Test-Driven Development (TDD)
Team C | Harini Saravanan | 2023-08-11 | Working on Returns Management /TestCases
Team C | Sheetal T A | 2023-08-11 | Working on Inventory TestCases
Team C | Nanditha M P | 2023-08-11 | Working on Resistry /TestCases |  |  | TDD
Team C | Nilay Mishra | 2023-08-11 | Working on Customer/ TestCases |  |  | Validations
Team C | Shravya C | 2023-09-11 | Working on API Gateway /TestCases | The team has completed CRUD operations on key requirements, including Order Management, Product and Promotions Management, Retail Store Inventory Management, Product Specifications, and Shipping Details, along with Login, Registration, API Gateway, and Registry. So far, 5 use cases have been completed, and 6 use cases are in progress. The goal is to complete a total of 11 use cases and then begin working on the logical r equirements and their Test-Driven Development (TDD) | As of now worked on API, Resistry, MS, and on login exceptions, Test cases, validation and Service Resistry and CRUD operations on Login and also worked on BRS document and so far we have achieved 10use cases | Exceptions
Team C | Harini Saravanan | 2023-09-11 | Working on Returns Management /TestCases |  | As of now completed cart and returns management with CRUD Operations. Now am working on test cases and validation ,Naming Standards need to be followed. Test case is working for delete and get operations. | CRUD
Team C | Sheetal T A | 2023-09-11 | Working on Inventory TestCases |  | Done with testing of all the crud operation in postman of retail inventory store management ,login page and all are working well.Started with Junit and tested all the eight test cases. | Use cases
Team C | Nanditha M P | 2023-09-11 | Working on Resistry /TestCases |  | As of now worked on Payment, registry, and also on Test cases. Now working on validation and Delete, update operation on Payment, Need to cover more implementations. | Test cases
Team C | Nilay Mishra | 2023-09-11 | Working on Customer/ TestCases |  | For now Completed with Curd operations and connection to the database on product and shipping specification which is the key requirements and also working on the TDD. | API Gatewat
Team C | Shravya C | 2023-10-11 | As mentioned almost covered 75% work and preparing for Sprint call-2 |  |  | Service registry
Team C | Harini Saravanan | 2023-10-11 | As mentioned almost covered 75% work and preparing for Sprint call-2 |  |  | Functional Requirement
Team C | Sheetal T A | 2023-10-11 | As mentioned almost covered 75% work and preparing for Sprint call-2
Team C | Nanditha M P | 2023-10-11 | As mentioned almost covered 75% work and preparing for Sprint call-2
Team C | Nilay Mishra | 2023-10-11 | As mentioned almost covered 75% work and preparing for Sprint call-2
Team C | Shravya C | 13/11/23 | After the Sprint call-2 working on feedback that was recieved.
Team C | Harini Saravanan | 13/11/23 | After the Sprint call-2 working on feedback that was recieved.
Team C | Sheetal T A | 13/11/23 | After the Sprint call-2 working on feedback that was recieved.
Team C | Nanditha M P | 13/11/23 | After the Sprint call-2 working on f eedback that was recieved.
Team C | Nilay Mishra | 13/11/23 | After the Sprint call-2 working on feedback that was recieved.
Team C | Shravya C | 15/11/23 | Completed with authorization and moving towards authentication. | The team has completed CRUD operations on key requirements, including Order Management, Product and Promotions Management, Retail Store Inventory Management, Product Specifications, and Shipping Details, along with Login, Registration, API Gateway, and Registry. So far, 10 use cases have been completed. and then begin working on the logical r equirements and their Test-Driven Development (TDD). The test cases for the use cases has been developed. The team is now working on the further feedbacks given during the sprint call 2. | As of now worked on API, Resistry, MS, and on login exceptions, Test cases, validation and Service Resistry and CRUD operations on Login and also worked on BRS document and so far we have achieved 10use cases
Team C | Harini Saravanan | 15/11/23 | Undersatnding the flow of project and working on authorization code |  | As of now completed cart and returns management with CRUD Operations. Now am working on test cases and validation ,Naming Standards need to be followed. Test case is working for delete and get operations.
Team C | Sheetal T A | 15/11/23 | Completed with authorization and moving towards authentication. |  | Done with testing of all the crud operation in postman of retail inventory store management ,login page and all are working well.Started with Junit and tested all the eight test cases.
Team C | Nanditha M P | 15/11/23 | Completed with authorization and moving towards authentication. |  | As of now worked on Payment, registry, and also on Test cases. Now working on validation and Delete, update operation on Payment, Need to cover more implementations.
Team C | Nilay Mishra | 15/11/23 | Completed with authorization and moving towards authentication. |  | For now Completed with Curd operations and connection to the database on product and shipping specification which is the key requirements and also working on the TDD.
Team C | Shravya C | 16/11/23 | Successfully authenticated and progressing further. | The team has completed CRUD operations on key requirements, including Order Management, Product and Promotions Management, Retail Store Inventory Management, Product Specifications, and Shipping Details, along with Login, Registration, API Gateway, and Registry. So far, 10 use cases have been completed. and then begin working on the logical r equirements and their Test-Driven Development (TDD). The test cases for the use cases has been developed. The team has worked on authentication, authorization and spring security
Team C | Harini Saravanan | 16/11/23 | Completed with spring security and moving forward
Team C | Sheetal T A | 16/11/23 | Successfully authenticated and progressing further.
Team C | Nanditha M P | 16/11/23 | Completed with spring security and moving forward
Team C | Nilay Mishra | 16/11/23 | Completed with spring security and moving forward
Team C | Shravya C | 17/11/23 | Successfully completed the project | The team has completed CRUD operations on key requirements, including Order Management, Product and Promotions Management, Retail Store Inventory Management, Product Specifications, and Shipping Details, along with Login, Registration, API Gateway, and Registry. So far, 10 use cases have been completed. and then begin working on the logical r equirements and their Test-Driven Development (TDD). The test cases for the use cases has been developed. The team has worked on authentication, authorization and spring security The team has successfully completed the project and the client was happy with the overall status of the project | Completed the project
Team C | Harini Saravanan | 17/11/23 | Successfully completed the project |  | Completed the project
Team C | Sheetal T A | 17/11/23 | Successfully completed the project |  | Completed the project
Team C | Nanditha M P | 17/11/23 | Successfully completed the project |  | Completed the project
Team C | Nilay Mishra | 17/11/23 | Successfully completed the project |  | Completed the project
Team C | Shravya C | 20/11/23 | Uploading all the codes into the folder and getting ready for final presentation
Team C | Harini Saravanan | 20/11/23 | Working on test cases document and getting ready for final presentation.
Team C | Sheetal T A | 20/11/23 | Working on traceability document and getting ready for final presentation
Team C | Nanditha M P | 20/11/23 | Uploading all the codes into the folder and getting ready for final presentation
Team C | Nilay Mishra | 20/11/23 | Working on final presentation ppt